## Optimus Syria - FB Controller
Milestones Feedback Controller
Project: Optimus Syria | [126 empty] | 2025-10-16
Name of Team | Main Task | Description | OCT | [30 empty] | NOV | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Collaborating Team | Items to be discussed
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Feedback Controller | Load principle measurements
Understand system dynamics and interfaces | bar: OCT 1 to OCT 21
| Interface freeze | Define data input/output to/from Loads & LAC | bar: OCT 14 to OCT 28
Load principle definitions completed. OpenFAST and ROSCO simulations initialized. | bar: OCT 21 to OCT 28
Input freeze for simulation
ROSCO input ready, reduced model complete | bar: OCT 28 to NOV 18
Feedback Controller | Design freeze
Final controller version completed | bar: NOV 18 to Dec 9
Final Report
Submit chapter on controller design | bar: Dec 9 to Jan 13
Final Presentation
Present controller function and performance | bar: Jan 13 to Jan 23
-
Note on Q7: Weekly Meeting
Note on DR7: Fainal presentaion
Final presentation