## Optimus Syria - RBS
Project: Optimus Syria |  |  | Milestone Plan of Team "Project Development"
Name of Team | Main Task | Description | OCT | [30 empty] | NOV | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Collaborating Team | Items to be discussed
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Project Development | Site Selection | 1. genral site analysis + Wind ressource analysis
| Detailed Site Analysis | 1. Legal Framework Analysis | [123 empty] | Grid Connection Team Storage Team | Grid Connection Storage space | bar: OCT 7 to Dec 2
2. QGIS Analysis | bar: OCT 21 to NOV 4
3. Environmental Impact Assessment | bar: OCT 28 to NOV 18
4. Land Leasing Agreements | bar: OCT 28 to NOV 25
5. Transportation Study | bar: NOV 18 to Dec 2
6. Grid Connection Plan | bar: Dec 2 to Dec 9
7. Conflict of Interests | bar: Dec 2 to Dec 24
| WindPro Simulation | 1. Project Setup | [123 empty] | Tbd | Tbd | bar: OCT 21 to NOV 4
2. Wind Resource Data | bar: NOV 4 to NOV 18
3. Layout Design | bar: NOV 18 to Dec 2
4. Compliance Optimization | bar: Dec 2 to Dec 16
5. Final Calculation | bar: Dec 16 to Dec 24
| Economic LCOE Calculation | 1. Setup of the calculation tool | [123 empty] | All The Teams!!! Regarding the costs! | Cost discussion | bar: OCT 21 to NOV 4
2. Collecting all the input parameters | bar: NOV 4 to NOV 18
3. Collecting all the cost of the components | bar: OCT 21 to Dec 2
4. Simulating the AEP | bar: NOV 18 to Dec 9
5. Calculating the LCOE | bar: Dec 9 to Dec 17
6. Final Economic Assessment | bar: Dec 18 to Dec 24
| Buffer Task | Buffer | bar: Dec 25 to Jan 26
Buffer | bar: Dec 25 to Jan 26
Buffer | bar: Dec 25 to Jan 26
Note on Q7: Weekly Meeting
Note on DR7: Fainal presentaion
Final presentation