## Optimus Syria - RBS
Milestones "Name of Team"
Project: Optimus Syria | [126 empty] | 2025-10-16
Name of Team | Main Task | Description | OCT | [30 empty] | NOV | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Collaborating Team | Items to be discussed
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Grid code Dev. | Prerequisites | Identify modes of grid operation according to DNV and PETE | bar: OCT 1 to OCT 6
Technological history from S. Heier's textbook | bar: OCT 1 to OCT 6
| Start of design | Hand calculations | bar: OCT 7 to OCT 20
SIMULINK | bar: OCT 7 to OCT 20
Feedback | bar: OCT 21 to OCT 27
Power factory | bar: OCT 28 to NOV 3
Feedback | bar: NOV 4 to NOV 10
Report draft | bar: NOV 11 to NOV 17
-
Note on Q7: Weekly Meeting
Note on DR7: Fainal presentaion
Final presentation